## Gantt
Board - Seismic Acquisition 3D Mapping System (by weeks)
|  |  | Oct-2024 | Oct-2024 | Oct-2024 | Oct-2024 | Oct-2024 | Oct-2024 | Oct-2024 | Oct-2024 | Oct-2024 | Oct-2024 | Nov-2024 | Nov-2024 | Nov-2024 | Nov-2024 | Nov-2024 | Nov-2024 | Nov-2024 | Nov-2024 | Nov-2024 | Nov-2024 | Nov-2024 | Nov-2024 | Nov-2024 | Nov-2024 | Nov-2024 | Nov-2024 | Nov-2024 | Nov-2024 | Nov-2024 | Nov-2024 | Nov-2024 | Nov-2024 | Nov-2024 | Nov-2024 | Nov-2024 | Nov-2024 | Nov-2024 | Nov-2024 | Nov-2024 | Nov-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Jan-2025 | Jan-2025 | Jan-2025 | Jan-2025 | Jan-2025 | Jan-2025 | Jan-2025 | Jan-2025 | Jan-2025 | Jan-2025 | Jan-2025 | Jan-2025 | Jan-2025 | Jan-2025 | Jan-2025 | Jan-2025 | Jan-2025 | Jan-2025 | Jan-2025 | Jan-2025 | Jan-2025 | Jan-2025 | Jan-2025 | Jan-2025 | Jan-2025 | Jan-2025 | Jan-2025 | Jan-2025 | Jan-2025 | Jan-2025
| Start | End | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Project Kick-off Meeting | 22-Oct-2024 | 24-Oct-2024 | 22: Project Kick-off Meeting (22-Oct-24 - 24-Oct-24); 23: Project Kick-off Meeting (22-Oct-24 - 24-Oct-24); 24: Project Kick-off Meeting (22-Oct-24 - 24-Oct-24)
Research and Requirement Gathering | 28-Oct-2024 | 30-Oct-2024 | 28: Research and Requirement Gathering (28-Oct-24 - 30-Oct-24); 29: Research and Requirement Gathering (28-Oct-24 - 30-Oct-24); 30: Research and Requirement Gathering (28-Oct-24 - 30-Oct-24)
Design Phase: System Architecture | 02-Nov-2024 | 06-Nov-2024 | 2: Design Phase: System Architecture (02-Nov-24 - 06-Nov-24); 3: Design Phase: System Architecture (02-Nov-24 - 06-Nov-24); 4: Design Phase: System Architecture (02-Nov-24 - 06-Nov-24); 5: Design Phase: System Architecture (02-Nov-24 - 06-Nov-24); 6: Design Phase: System Architecture (02-Nov-24 - 06-Nov-24)
Documentation | 02-Nov-2024 | 06-Dec-2024 | 2: Documentation (02-Nov-24 - 06-Dec-24); 3: Documentation (02-Nov-24 - 06-Dec-24); 4: Documentation (02-Nov-24 - 06-Dec-24); 5: Documentation (02-Nov-24 - 06-Dec-24); 6: Documentation (02-Nov-24 - 06-Dec-24); 7: Documentation (02-Nov-24 - 06-Dec-24); 8: Documentation (02-Nov-24 - 06-Dec-24); 9: Documentation (02-Nov-24 - 06-Dec-24); 10: Documentation (02-Nov-24 - 06-Dec-24); 11: Documentation (02-Nov-24 - 06-Dec-24); 12: Documentation (02-Nov-24 - 06-Dec-24); 13: Documentation (02-Nov-24 - 06-Dec-24); 14: Documentation (02-Nov-24 - 06-Dec-24); 15: Documentation (02-Nov-24 - 06-Dec-24); 16: Documentation (02-Nov-24 - 06-Dec-24); 17: Documentation (02-Nov-24 - 06-Dec-24); 18: Documentation (02-Nov-24 - 06-Dec-24); 19: Documentation (02-Nov-24 - 06-Dec-24); 20: Documentation (02-Nov-24 - 06-Dec-24); 21: Documentation (02-Nov-24 - 06-Dec-24); 22: Documentation (02-Nov-24 - 06-Dec-24); 23: Documentation (02-Nov-24 - 06-Dec-24); 24: Documentation (02-Nov-24 - 06-Dec-24); 25: Documentation (02-Nov-24 - 06-Dec-24); 26: Documentation (02-Nov-24 - 06-Dec-24); 27: Documentation (02-Nov-24 - 06-Dec-24); 28: Documentation (02-Nov-24 - 06-Dec-24); 29: Documentation (02-Nov-24 - 06-Dec-24); 30: Documentation (02-Nov-24 - 06-Dec-24); 1: Documentation (02-Nov-24 - 06-Dec-24); 2: Documentation (02-Nov-24 - 06-Dec-24); 3: Documentation (02-Nov-24 - 06-Dec-24); 4: Documentation (02-Nov-24 - 06-Dec-24); 5: Documentation (02-Nov-24 - 06-Dec-24); 6: Documentation (02-Nov-24 - 06-Dec-24)
Development Environment Setup | 07-Nov-2024 | 07-Nov-2024 | 7: Development Environment Setup (07-Nov-24 - 07-Nov-24)
Development | 08-Nov-2024 | 25-Nov-2024 | 8: Development (08-Nov-24 - 25-Nov-24); 9: Development (08-Nov-24 - 25-Nov-24); 10: Development (08-Nov-24 - 25-Nov-24); 11: Development (08-Nov-24 - 25-Nov-24); 12: Development (08-Nov-24 - 25-Nov-24); 13: Development (08-Nov-24 - 25-Nov-24); 14: Development (08-Nov-24 - 25-Nov-24); 15: Development (08-Nov-24 - 25-Nov-24); 16: Development (08-Nov-24 - 25-Nov-24); 17: Development (08-Nov-24 - 25-Nov-24); 18: Development (08-Nov-24 - 25-Nov-24); 19: Development (08-Nov-24 - 25-Nov-24); 20: Development (08-Nov-24 - 25-Nov-24); 21: Development (08-Nov-24 - 25-Nov-24); 22: Development (08-Nov-24 - 25-Nov-24); 23: Development (08-Nov-24 - 25-Nov-24); 24: Development (08-Nov-24 - 25-Nov-24); 25: Development (08-Nov-24 - 25-Nov-24)
Output - Generate Multiplicity and Offset Curves | 26-Nov-2024 | 28-Nov-2024 | 26: Output - Generate Multiplicity and Offset Curves (26-Nov-24 - 28-Nov-24); 27: Output - Generate Multiplicity and Offset Curves (26-Nov-24 - 28-Nov-24); 28: Output - Generate Multiplicity and Offset Curves (26-Nov-24 - 28-Nov-24)
Testing | 29-Nov-2024 | 03-Dec-2024 | 29: Testing (29-Nov-24 - 03-Dec-24); 30: Testing (29-Nov-24 - 03-Dec-24); 1: Testing (29-Nov-24 - 03-Dec-24); 2: Testing (29-Nov-24 - 03-Dec-24); 3: Testing (29-Nov-24 - 03-Dec-24)
Review and Validation of Results | 03-Dec-2024 | 05-Dec-2024 | 3: Review and Validation of Results (03-Dec-24 - 05-Dec-24); 4: Review and Validation of Results (03-Dec-24 - 05-Dec-24); 5: Review and Validation of Results (03-Dec-24 - 05-Dec-24)
Final Project Review and Submission | 07-Dec-2024 | 07-Dec-2024 | 7: Final Project Review and Submission (07-Dec-24 - 07-Dec-24)