PROJECT PLAN

Version 3.0

A Project On

SEISMIC ACQUISITION 3D MAPPING SYSTEM

GROUP – 2 (METAMINDS)

NANDEESWAR BADUGU

SAITEJA SIRIPURAPU

JAYTHRI PUPPALA

SAI KISHORE BHADRAGIRI

Table of Contents

VERSION TABLE2

PROJECT OVERVIEW2

IS/IS NOT2

RISK ANALYSIS AND MITIGATION3

HARDWARE AND SOFTWARE REQUIREMENTS3

PROJECT SCHEDULE3

KEY DELIVERABLES4

ACTIVITY BAR CHART5

FLEXIBILITY MATRIX5

CONCLUSION6

- VERSION TABLE

| Version | Date | Author | Description of Changes | Reviewed By |
| --- | --- | --- | --- | --- |
| 1.1 | 11/04/2024 | Saiteja/Jaythri | Initial draft of the project plan. | Mr. Thomas Dillon J |
| 1.2 | 11/11/2024 | Saiteja/Jaythri | Updated flexibility matrix and version control. | Mr. Thomas Dillon J |
| 1.3 | 11/18/2024 | Saiteja/Jaythri | Updated Project Timeline and link to Monday.com | Mr. Thomas Dillon J |
| 2.0 | 11/26/2024 | Saiteja/Jaythri | Added cover page and trimmed/added data wherever required as per comments | Mr. Thomas Dillon J |
| 3.0 | 11/28/2024 | Saiteja/Jaythri | Updated project timeline | Yet to Review |

- PROJECT OVERVIEW

The Seismic Acquisition 3D Mapping System aims to create a sophisticated software-based solution for the collection and analysis of seismic data. This system will enhance the accuracy and efficiency of seismic mapping by generating detailed multiplicity and offset curves, crucial for geophysical exploration. The goal of this project is to calculate and analyze the multiplicity and offset curve in a seismic survey, given the distance between geophones and the range of sources. These parameters are critical for optimizing the survey design and ensuring proper subsurface coverage for high-quality 3D seismic imaging.

- IS / IS NOT

IS:

- A software solution for seismic data acquisition, processing, and visualization.

- Focused on generating multiplicity and offset curves.

- Designed to operate within existing seismic acquisition frameworks.

- Aimed at enhancing subsurface imaging quality for geophysical exploration

- Supporting real-time visualization of seismic data

- Compliant with industry standards for data privacy and security

IS NOT:

- A hardware-based seismic data collection system

- A physical field study or examination.

- A standalone system without integration capabilities.

- Focused on providing geophysical interpretations or analysis expertise

- Designed for long-term data storage or archival solutions

- Intended to generate reports on compliance or regulatory requirements

- RISK ANALYSIS AND MITIGATION

- Software Development Delays: Risk of not meeting deadlines due to unforeseen technical challenges.

Mitigation: Implement agile development practices with iterative testing and regular check-ins.

- Data Simulation Inaccuracies: Potential discrepancies between simulated and actual data.

Mitigation: Use validated simulation models and conduct rigorous testing.

- Algorithm Performance Issues: Algorithms may not perform as expected under certain conditions.

Mitigation: Carry out performance testing early in development to identify and address issues.

- Resource Availability: Potential unavailability of key personnel or resources.

Mitigation: Cross-train team members to ensure coverage.

## HARDWARE AND SOFTWARE REQUIREMENTS

Hardware Requirements:

- Processor: i5 and above

- RAM: 8 GB and above.

- Hard disk: more than 30 GB in local

Software Requirements:

- Python 3.7 or later

- Framework: Django

- PROJECT SCHEDULE

| Start Date | End Date | Activity | Responsible | Deliverables |
| --- | --- | --- | --- | --- |
| 22-Oct-2024 | 24-Oct-2024 | Project Kick-off Meeting | All | Agenda, minutes, project charter. |
| 28-Oct-2024 | 30-Oct-2024 | Research and Requirement Gathering | All | Requirements document, user personas, research summary. |
| 02-Nov-2024 | 06-Nov-2024 | Design Phase: System Architecture | Jaythri, Kishore | Architecture diagrams, design document, wireframes. |
| 07-Nov-2024 | 07-Nov-2024 | Development Environment Setup | All | Setup guide, tools list, verification report. |
| 08-Nov-2024 | 28-Nov-2024 | Development | All | Source code, code documentation, progress reports. |
| 29-Nov-2024 | 01-Dec-2024 | Testing | Jaythri, Saiteja | Test plan, test cases, results report. |
| 02-Dec-2024 | 02-Dec-2024 | Review and Validation of Results | All | Review validation report, feedback summary. |
| 02-Nov-24 | 04-Dec-24 | Documentation | All | Document Plan |
| 05-Dec-2024 | 05-Dec-2024 | Final Project Review and Submission | All | Final report, submission package, presentation slides. |

- KEY DELIVERABLES

- Software Requirements Specification Document: Detailed documentation of functional and non-functional requirements, including specifications for multiplicity and offset curve calculation, data collection parameters, and analysis requirements.

- Design Document: Comprehensive design of the software solution, including data flow diagrams, system components, and integration points for efficient processing of seismic data.

- Multiplicity and Offset Calculation Engine: Core algorithms and logic for calculating multiplicity and offset curves based on given geophone distances and source ranges, ensuring accurate survey results.

- System Testing and Validation Reports: Comprehensive testing documentation, covering unit, integration, and system testing to validate functionality, performance, and data accuracy.

- Final Project Report and Presentation Package: A consolidated report summarizing the project’s goals, methods, outcomes, and conclusions, along with presentation slides for final review.

- ACTIVITY BAR CHART

Link 1:

Monday.com

Link 2:

Monday.com

- FLEXIBILITY MATRIX

| Aspect | Least Flexible | Moderate Flexible | Most Flexible |
| --- | --- | --- | --- |
| Schedule |  | ✔️ |  |
| Scope |  |  | ✔️ |
| Resources | ✔️ |  |  |

- CONCLUSION

This comprehensive project plan outlines the key components of the Seismic Acquisition 3D Mapping System. By clearly defining the project's scope, deliverables, risks, and flexibility, we aim to successfully deliver accurate multiplicity and offset curves within the established timeline.